## Test_Cases
TC ID | Module | Scenario | Steps | Expected Result | Actual Result | Status
TC_001 | Login | Valid login | Enter valid email/password | User logs in successfully | User redirected to account page | Pass
TC_002 | Login | Invalid password | Enter wrong password | Error message shown | Error displayed correctly | Pass
TC_003 | Login | Invalid email format | Enter abc@abc | Validation message shown | Form accepted invalid email | Fail
TC_004 | Signup | New registration | Fill all mandatory fields | Account created | Account created successfully | Pass
TC_005 | Search | Search “laptop” | Enter keyword and search | Relevant products displayed | Mixed unrelated items shown | Fail
TC_006 | Cart | Add item to cart | Click Add to cart | Item added to cart | Added successfully | Pass
TC_007 | Cart | Update quantity | Change qty from 1 to 2 | Quantity updates immediately | Updated only after refresh | Fail
TC_008 | Cart | Remove item | Remove selected item | Item removed | Removed correctly | Pass
TC_009 | Checkout | Mandatory address validation | Leave address blank | Validation error shown | Error shown | Pass
TC_010 | Checkout | Valid shipping details | Enter address and continue | Proceed to payment | Proceeded successfully | Pass
TC_011 | Payment | Select payment on Chrome | Choose payment method | Payment page loads | Loaded successfully | Pass
TC_012 | Payment | Select payment on Firefox | Choose payment method | Payment page loads | Continue button inactive | Fail

## Bug_Reporting
BugId | Description | Steps to reproduce bug | Environment | Expexted Output | Actual Output | Severity | Priority
Bug-101 | Application allows invalid email input and proceeds to authentication. | 1.Open login page 2.Enter email abc@abc 3.Enter valid password 4.Click login | OS: Windows 10 Browser: Google Chrome | Validation message should appear for invalid email format. | System accepts invalid email. | Medium | High
Bug-102 | Cart quantity updates only after refresh | 1.Add item to cart 2.Change quantity from 1 to 2 3.Click update | Browser: Google Chrome | Quantity should update instantly. | Page refresh required. | High | High
Bug-103 | Search returns unrelated products | 1.Search “laptop” 2.Submit query | Browser:Mozilla Firefox | Laptop-related items only. | Unrelated accessories shown. | Medium | Medium
Bug-104 | Payment continue button disabled in Firefox | 1.Add product 2.Checkout 3.Payment step | Browser:Mozilla Firefox | Continue button enabled. | Button disabled. | Critical | High
Bug-105 | Product image broken on product details page | 1.Open Demo Web Shop Navigate to Books category 2.Select any product (for example, “Computing and Internet”) 3.Open the product details page 4.Observe the main product image area | Browser: Google Chrome | Product image should load correctly and display the selected item. | Broken image icon appears,product image does not load. | Medium | Medium